## Project Status Dashboard
Dashboard |  |  | Project Status Dashboard
| Project Status |  | Completed |  | 5% |  | Outstanding Issues
| Ongoing Activities: 1 |  |  | Project Plan |  | Click on the gantt chart to see it in detail
| Activity | % done
| CFO Interview | 0%
| Requirement write up | 0%
| Product identification | 0%
| 0 | 0%
| 0 | 0%
Top 5 Issues
Agree requirements
Af
Training in Canada
Dashboard delivery plans
Business Testers
| Burndown Chart |  |  |  |  | Project Timeline
Project below this are dependant upon the product selection
Project below this are dependant upon the product selection

## Gantt Chart Template
Project Plan - Gantt Chart Template
|  | Planned |  | Actual |  | % | Show Gantt for | [5 empty] | Planned | [5 empty] | Show Status? |  |  |  |  | █ |  |  |  | What is current week? | [8 empty] | 2
# | List of Activities | Start | Dur | Start | Dur | Done | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
1 | Management presentation | 1 | 1 | 1 | 1 | 100% | █
2 | CFO interview | 3 | 1 | 0 | 0 | 0%
3 | Requirements write up | 3 | 1 | 0 | 0 | 0%
4 | COO review requirements | 4 | 1 | 0 | 0 | 0%
5 | President Interview | 5 | 1 | 0 | 0 | 0%
6 | Prometic Requirements Doc | 6 | 1 | 0 | 0 | 0%
7 | Review of products | 7 | 2 | 0 | 0 | 0%
8 | Create demo apps | 8 | 2 | 0 | 0 | 0%
9 | COO sign off | 10 | 1 | 0 | 0 | 0%
10 | Produce Quotes | 11 | 1 | 0 | 0 | 0%
11 | Sign off Quotes | 12 | 2 | 0 | 0 | 0%
12 | Transfer Syspro to FTP | 11 | 3 | 0 | 0 | 0%
13 | Transfer Syspro to Azure | 13 | 2 | 0 | 0 | 0%
14 | Deploy Reporting DB to Azure | 14 | 1 | 0 | 0 | 0%
15 | Define user groups | 13 | 1 | 0 | 0 | 0%
16 | Get Training Costs | 11 | 3 | 0 | 0 | 0%
17 | Define network security | 12 | 3 | 0 | 0 | 0%
18 | Define publication route | 13 | 1 | 0 | 0 | 0%
19 | Agree division of labour | 14 | 1 | 0 | 0 | 0%
20 | Set up of users and user groups | 14 | 1 | 0 | 0 | 0%
21 | Provision of application servers | 15 | 2 | 0 | 0 | 0%
22 | Provision of firewall | 15 | 2 | 0 | 0 | 0%
23 | provision of external proxy server | 15 | 2 | 0 | 0 | 0%
24 | Set up of application server | 17 | 1 | 0 | 0 | 0%
25 | set up of Qlik on proxy | 17 | 1 | 0 | 0 | 0%
26 | Deploy first report to test | 17 | 1 | 0 | 0 | 0%
27 | User Training | 18 | 1 | 0 | 0 | 0%
28 | testing by users | 18 | 3 | 0 | 0 | 0%
29 | deployment to live | 20 | 1 | 0 | 0 | 0%
30 | Activity 30 | 0 | 0 | 0 | 0 | 0%
31 | Activity 31 | 0 | 0 | 0 | 0 | 0%
32 | Activity 32 | 0 | 0 | 0 | 0 | 0%
33 | Activity 33 | 0 | 0 | 0 | 0 | 0%
34 | Activity 34 | 0 | 0 | 0 | 0 | 0%
35 | Activity 35 | 0 | 0 | 0 | 0 | 0%
36 | Activity 36 | 0 | 0 | 0 | 0 | 0%
37 | Activity 37 | 0 | 0 | 0 | 0 | 0%
38 | Activity 38 | 0 | 0 | 0 | 0 | 0%
39 | Activity 39 | 0 | 0 | 0 | 0 | 0%
40 | Activity 40 | 0 | 0 | 0 | 0 | 0%

## Backlog
Project Plan - Backlog
# | Activity | Task # | Task | Assigned To | Due Date | Count | Status | Details
1 | Management presentation | 1 | Presentation to COO and CFO of existing plans | CJ/HM | 2016-02-29 | 1 | Complete | COO stated costs were too much and design was not in line with expectations
2 | CFO interview | 2 | Capture requirements of CFO and FPA director | CJ/HM | 2016-03-16 | 1 | Outstanding | Awaiting CFO visit to UK
3 | Requirements write up | 3 | Requirements write up into project documentation | CJ | 2016-03-18 | 1 | Outstanding | Awaiting Task 2
4 | COO review requirements | 4 | Present CFO req's to COO for review and additional requirements | CJ/HM | 2016-03-25 | 1 | Outstanding | Awaiting Task 3
5 | President Interview | 5 | Present CFO and COO's reqs to present and capture additional requirements | CJ/HM | 2016-04-01 | 1 | Outstanding | Awaiting Task 4
6 | Prometic Requirements Doc | 6 | Requirements write up into project documentation | CJ | 2016-04-08 | 1 | Outstanding | Awaiting Task 5
7 | Review of products | 7 | Find products to review and compare to requirements | CJ | 2016-04-22 | 1 | Outstanding | Awaiting Task 6
8 | Create demo apps | 8 | Create/Source demonstration applications | CJ | 2016-04-29 | 1 | Outstanding | Awaiting Task 6
9 | COO sign off | 9 | Presentation to COO and CFO of demo apps for sign off | CJ | 2016-05-06 | 1 | Outstanding | Awaiting Task 8
10 | Produce Quotes | 10 | Define number of users | CJ/HM |  | 1 | Complete | 5 users + 50 hours of access per month
10 | Produce Quotes | 11 | Agree level of support | CJ/HM |  | 1 | Complete | daily checks and support
10 | Produce Quotes | 12 | Agree infrastructure location | CJ/HM |  | 1 | Complete | Prometic's Azure platform
10 | Produce Quotes | 13 | Provide sliding scale of server requirements | Differentia |  | 1 | Complete
10 | Produce Quotes | 14 | Provide Quote for Qlik licenses and setup | Differentia |  | 1 | Complete
10 | Produce Quotes | 15 | Provide Quote for Azure infrastructure | HM |  | 1 | Complete
11 | Sign off Quotes | 16 | Present Quotes to BP/GW/DF | CJ/HM |  | 1 | Outstanding | Awaiting Task 6
11 | Sign off Quotes | 17 | Sign off Quotes | BP |  | 1 | Outstanding | Awaiting Task 7
12 | Transfer Syspro to FTP | 18 | Request backup and transfer | HM |  | 1 | Complete | Request sent 26/02
12 | Transfer Syspro to FTP | 19 | Action and automate transfer | K3 |  | 1 | Outstanding
13 | Transfer Syspro to Azure | 20 | Grant CJ access to Azure | IT |  | 1 | Outstanding
13 | Transfer Syspro to Azure | 21 | Write job to import files | CJ |  | 1 | Outstanding | Awaiting Task 11
13 | Transfer Syspro to Azure | 22 | define and build error reports | CJ |  | 1 | Outstanding | Awaiting Task 12
14 | Deploy Reporting DB to Azure | 23 | Deploy Reporting DB to Azure | CJ |  | 1 | Outstanding | Awaiting Task 13
15 | Define user groups | 24 | Define different types of reports | CJ |  | 1 | Outstanding
15 | Define user groups | 25 | Define different levels of data | CJ |  | 1 | Outstanding
15 | Define user groups | 26 | Choose first deployment users | ? |  | 1 | Outstanding
15 | Define user groups | 27 | Choose Super Users | ? |  | 1 | Outstanding
15 | Define user groups | 28 | Assign users to groups | ? |  | 1 | Outstanding
16 | Get Training Costs | 29 | Get Training Costs | CJ |  | 1 | Outstanding
17 | Define network security | 30 | Review of network diagram by IT & Differentia | IT |  | 1 | Outstanding
18 | Define publication route | 31 | Agree change control form | CJ/HM |  | 1 | Outstanding
18 | Define publication route | 32 | Agree access to test server | CJ/HM |  | 1 | Outstanding
18 | Define publication route | 33 | Agree sign off and go live process | CJ/HM |  | 1 | Outstanding
19 | Agree division of labour | 34 | Define what infrastructure exists and what needs to be setup | IT |  | 1 | Outstanding
19 | Agree division of labour | 35 | define at what point Differentia take over configuration | IT |  | 1 | Outstanding
19 | Agree division of labour | 36 | Define internal issues vs those to be raised to Differentia | IT/CJ |  | 1 | Outstanding
20 | Set up of users and user groups | 37 | Create users and groups in Azure AD | IT |  | 1 | Outstanding | Awaiting Task 19
21 | Provision of application servers | 38 | Provision of live server | IT |  | 1 | Outstanding | Awaiting Task 8
21 | Provision of application servers | 39 | Provision of test server | IT |  | 1 | Outstanding | Awaiting Task 8
22 | Provision of firewall | 40 | Provision of firewall | IT |  | 1 | Outstanding | Awaiting Task 8
23 | provision of external proxy server | 41 | provision of external proxy server | IT |  | 1 | Outstanding | Awaiting Task 8
24 | Set up of application server | 42 | Set up of live server | Differentia |  | 1 | Outstanding | Awaiting Task 29
24 | Set up of application server | 43 | Set up of test server | Differentia |  | 1 | Outstanding | Awaiting Task 30
25 | set up of Qlik on proxy | 44 | set up of Qlik on proxy | Differentia |  | 1 | Outstanding | Awaiting Task 32
26 | Deploy first report to test | 45 | Deploy first report to test | CJ |  | 1 | Outstanding | Awaiting Task 35
27 | User Training | 46 | Agree approach internal vs external | ? |  | 1 | Outstanding | Awaiting Task 36
28 | testing by users | 47 | Internal testing - access to system | CJ/HM |  | 1 | Outstanding | Awaiting Task 37
28 | testing by users | 48 | define users to conduct testing | CJ/HM |  | 1 | Outstanding | Awaiting Task 38
28 | testing by users | 49 | User testing - report data and functionality | ? |  | 1 | Outstanding | Awaiting Task 39
29 | deployment to live | 50 | following sign off, move report to live server | Differentia |  | 1 | Outstanding | Awaiting Task 40
Project below this are dependant upon the product selection

## Issue Tracker
Issue Tracker Template
Date
# | Issue | Priority | Open | Close | Comments
1 | Training in Canada | High | 2016-02-26 |  | How to deliver user training in Canada
2 | Dashboard delivery plans | Low
3 | Business Testers | Medium | 2016-02-26 |  | Which users will be involved in testing - that have time to test?
4 | Product Selection | High
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## Burndown Chart
Burn down chart
Deliverable Burn Down
| Burned down |  | Balance |  | Daily Completed
Day | Planned | Actual | Planned | Actual
0 |  |  | 44 | 44 | #N/A
1 | 1 | 1 | 43 | 43 | 1
2 | 0 | 0 | 43 | 43 | 0
3 | 2 |  | 41 | #N/A | #N/A
4 | 1 |  | 40 | #N/A | #N/A
5 | 1 |  | 39 | #N/A | #N/A
6 | 1 |  | 38 | #N/A | #N/A
7 | 1 |  | 37 | #N/A | #N/A
8 | 2 |  | 35 | #N/A | #N/A
9 | 1 |  | 34 | #N/A | #N/A
10 | 1 |  | 33 | #N/A | #N/A
11 | 3 |  | 30 | #N/A | #N/A
12 | 4 |  | 26 | #N/A | #N/A
13 | 7 |  | 19 | #N/A | #N/A
14 | 5 |  | 14 | #N/A | #N/A
15 | 3 |  | 11 | #N/A | #N/A
16 | 3 |  | 8 | #N/A | #N/A
17 | 3 |  | 5 | #N/A | #N/A
18 | 2 |  | 3 | #N/A | #N/A
19 | 1 |  | 2 | #N/A | #N/A
20 | 2 |  | 0 | #N/A | #N/A

## Data
Enter Project Status |  | Enter the Project Milestone Data Here |  |  | Top 5 Issues
Overall Project Status | Amber | Date | Milestone if any | Height | Issue | Dummy
Overall Project Progress | 5% | 2016-02-01 |  |  | Agree requirements | 0
|  | 2016-02-01 |  |  | Af | 0
Enter Activity Details |  | 2016-03-01 |  |  | Training in Canada | 0
|  | 2016-03-01 |  |  | Dashboard delivery plans | 0
|  | 2016-04-01 |  |  | Business Testers | 0
Ongoing Activities | 1 | 2016-05-01 |  |  |  | 0
|  | 2016-06-01 |  |  |  | 0
List of Activities |  | 2016-07-01 |  |  |  | 0
|  | 2016-08-01 |  |  |  | 0
Activity | Completion | 2016-09-01 |  |  |  | 0
CFO Interview | 0% | 2016-10-01 |  |  |  | 0
Requirement write up | 0% | 2016-10-01 |  |  |  | 0
Product identification | 0%
Note on K3: Donot edit this

## Calculations (hidden)
Open Issue Summary
High | 2
Medium | 1
Low | 1

## Legend (hidden)
Types of Gantt | Gantt Chart Symbols
Planned | █
Actual | ○
↓