## Worklist
Status | # | Type | Category | Name | Request Date | Requested By | Description | Tester | Last Update | Notes
New | 1 | Documents | New | Inspection Report | 2016-02-01 | Georgia Gerontakos | Create a document to allow data to be populated in QC inspection | Francis Vaillancourt | 2016-02-02 | Specification to be written and agreed
In Progress | 20 | Documents | Replace existing report | Commercial and Transporter Invoice | 2015-12-01 | Ross Moore | Document to pick up new fields | Ross Moore | 2016-02-01 | Awaiting details from Hassan, initial changes made to the report
In Progress | 20 | Crystal | New Report | QC KPI Report | 2015-10-01 | Andrew Hafford | Report to analyse throughput KPI’s | Andrew | 2016-02-01 | Changes following feedback being developed
Awaiting Testing | 60 | Crystal | New Report | Ledger Query | 2015-10-01 | Liz Collins | Allow querying of ledger journals by period and by mappings as provided by LC | Liz | 2015-10-01
Awaiting Testing | 60 | Crystal | Replace existing report | AP Aged Analysis | 2015-10-01 | Kirsty Wells | Rewrite Aged Analysis reports provided in Syspro | Kirsty | 2015-10-10 | Chasing testing
Awaiting Testing | 60 | Crystal | New Report | Labour Ledger Comparison | 2015-10-01 | David Franklin | Comparison of Labour entered into Syspro and the corresponding ledger amounts | Liz | 2015-10-16 | Awaiting testing and feedback to further develop
Awaiting Testing | 60 | Crystal | New Report | Purchase Order Details | 2015-09-01 | Liz Collins | details of all purchase orders with supplier, item, cost and requisition details | Liz | 2015-11-01
Awaiting Testing | 60 | Crystal | Replace existing report | GRN Unpaid Assets | 2015-10-01 | - | Replace Logi-Solutions reports with validated reports | Bianca | 2015-12-17 | Sent to Bianca for sign off on 17th December
Awaiting Testing | 60 | Crystal | New Report | Purchase Order E-signatures | 2015-09-01 | Liz Collins | details of all changes made to purchase orders | Liz | 2016-02-01 | Changes made following testing
Awaiting Testing | 60 | Crystal | New Report | Picklist Reports | 2015-11-01 | Bryan Vickers | Details of stock required for manufacturing processes | Bryan | 2016-02-01 | Testing on hold - BV
Awaiting Testing | 60 | Dashboard | Project | Uncommitted transactions | 2016-02-01 | Greg Weaver | Dashboard showing PO's and Requisitions with due dates | Liz | 2016-02-01
Awaiting Testing | 60 | Crystal | Change to report | Payment Run | 2016-02-01 | Bianca Vasquez | add non-invoice transactions | Bianca | 2016-02-01
Awaiting Testing | 60 | Crystal | Change to report | Payment Run | 2016-02-01 | Bianca Vasquez | rewrite report to run for invoice numbers | Bianca | 2016-02-01 | Sent to BV for testing 16/02
Awaiting Testing | 60 | Crystal | New Report | Supplier Changes report | 2016-02-01 | Jacqueline Richard | Report to show changes made to suppliers | Jacqueline | 2016-02-03 | Sent basic data to Jacqueline for her to review
Awaiting Testing | 60 | Crystal | New Report | Manufacturing KPI | 2015-12-01 | Ross Moore | Report to show if shipping is completed by the requested shipping date | Ross Moore | 2016-02-04 | sent to RM 12/2 for testing
Awaiting Testing | 60 | Crystal | New Report | Outstanding Purchase Order Report | 2016-01-01 | Matt Fantham | Replacement for meeting review report | Matt Fantham | 2016-03-01 | Sent to MF for testing
Awaiting Testing | 60 | Crystal | New Report | Goods in Inspection | 2016-01-01 | Matt Fantham | Replacement for QC report | Matt Fantham | 2016-03-01 | Sent to MF for testing
Awaiting Testing | 60 | Crystal | Replace existing report | Purchase Order Changes | 2015-10-01 | - | Replace Logi-Solutions reports with validated reports | Benjamin
On Hold | 70 | Crystal | Replace existing report | AP Unpaid Assets | 2015-10-01 | - | Replace Logi-Solutions reports with validated reports | Bianca | 2016-01-01 | Need to discuss with hassan adding field to GL table
On Hold | 70 | Crystal | Replace existing report | Requisition Details | 2015-10-01 | - | Replace Logi-Solutions reports with validated reports | Benjamin | 2016-01-01 | Changes to be made following tidy up of Syspro by K3
On Hold | 70 | Dashboard | Project | Budget vs Actuals Actual vs Actuals | 2015-11-01 | Dominic Lefebvre | Build dashboard based off of Syspro budget and General ledger | Dominic | 2016-02-03 | Need to liaise with Dominic following paternity leave and development in QlikSense
On Hold | 70 | Crystal | Change to report | Payment Run | 2016-02-01 | Bianca Vasquez | add supplier currency | Bianca
Signed Off | 90 | Crystal | New Report | Sales Order Status | 2015-09-01 | Liz/Shrinal | Details of Sales Orders raised | Liz | 2015-10-01 | Signed off
Signed Off | 90 | Crystal | New Report | Sales By Job | 2015-10-01 | Shrinal Inamdar | Details of Sales with batch information | Shrinal | 2015-10-01 | Signed off
Signed Off | 90 | Crystal | Replace existing report | Payment Run | 2015-10-01 | - | Replace Logi-Solutions reports with validated reports | Bianca | 2016-01-01 | Signed off
Signed Off | 90 | Crystal | Change to report | RetestingLots | 2016-01-01 | Nadia Amaral | Add Unit Cost | Nadia Amaral | 2016-01-01 | Signed off
Signed Off | 90 | Dashboard | Project | Compare Dashboard tools | 2015-10-01 | - | Review of dashboard software | Chris | 2016-01-12 | Report written and sent to David & Jacqueline
Signed Off | 90 | Crystal | New Report | Requisition Users | 2015-10-01 | Liz Collins | Details of all requisition users and their level of permission. | Liz | 2016-02-01 | Signed off
Signed Off | 90 | Crystal | Replace existing report | Open Purchase Orders | 2015-10-01 | - | Replace Logi-Solutions reports with validated reports | Liz | 2016-02-01 | Signed off
Signed Off | 90 | Crystal | New Report | Job Lot Breakdown | 2015-10-01 | David Franklin | Details of Labour, stock and sales relating to Job | Liz | 2016-02-01 | Signed off
Signed Off | 90 | Crystal | New Report | Stock Levels | 2015-10-01 | Liz Collins | Details of all stock held across all warehouses | Liz | 2016-02-01 | Signed off
Signed Off | 90 | Crystal | Change to report | Payment Run | 2016-02-01 | Bianca Vasquez | Remove non-invoice journal transactions | Bianca | 2016-02-01 | Signed off
Signed Off | 90 | Crystal | New Report | Lot Traceability | 2016-01-01 | Matt Fantham | Search by lot number and show all transactions | Matt Fantham | 2016-02-11 | Signed off
Signed Off | 90 | Crystal | New Report | Batch Profitability | 2015-10-01 | David Franklin | Details of profit from batches over period | David
Signed Off | 90 | Crystal | New Report | Fixed Asset List | 2015-10-01 | Kirsty Wells | List of all fixed assets | Kirsty |  | Signed off
Cancelled | 99 | Crystal | New Report | General Ledger Map Check | 2015-10-01 | Liz Collins | Show details of the accuracy of the ledger maps provided by LC | Liz | 2015-10-01 | Cancelled report - covered under Actual vs budget dashboard
Cancelled | 99 | Crystal | New Report | BudgetTest | 2015-10-01 | Liz Collins | Actuals vs Budget | Liz | 2015-10-01 | Replaced with work with Dominic
Cancelled | 99 | Crystal | New Report | Purchase Order Invoices | 2015-10-01 | Liz Collins | details of all purchase orders and invoices received for them | Liz | 2015-11-01 | cancelled report as no longer required
Cancelled | 99 | Crystal | New Report | Bank Accounts | 2015-10-01 | David Franklin | Latest bank balances across all companies | Kirsty | 2016-01-01 | Tested by Kirsty, to be included in Exec dashboard
Cancelled | 99 | Crystal | New Report | Accounts Receivable customers | 2015-10-01 | Kirsty Wells | Report to look at newly added customers | Liz | 2016-02-01 | cancelled report as no longer required
Cancelled | 99 | Crystal | New Report | Stock Levels by Lot | 2015-10-01 | Liz Collins | Report to look at all stock by lot numbers | Liz | 2016-02-01 | cancelled report as doesn't provide detail needed
Cancelled | 99 | Crystal | New Report | Supplier Stock Traceability | 2016-02-01 | Hassan Mamdani | Report to identify how and where suppliers stocks are used | Hassan Mamdani | 2016-02-04 | This report is covered by the Lot Traceability report

## Redtag log
As part of the Lean Six Sigma review, red tags are to be added to all stored procedures to monitor when they are being used
SchemaName | ProcedureName | ParameterDetails | DatabaseName | O/S | TBD
Report | UspResults_WipSubJobStock | [@Company], [@MasterJob], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_JobStockDetails | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_RequisitionUsers | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_PaymentRunVerify | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_SalesOrderKPI | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_GenJournalDetails | [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_CompaniesCurrencyLatestExchangeRates | [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_LotTraceability | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_PurchaseOrdersHistory | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_InvoiceRunVerify | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_JournalDetails | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_AllPosAndReqs | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_RequisitionStatus | [@Company], [@RedTagType], [@RedTagUse] | BlackBox | 1
Report | UspResults_FixedAssets | [@Company] | BlackBox | 0 | 1
Report | UspResults_ApInvoicesWithPaymentDetails | [@Company] | BlackBox | 0 | 1
Report | UspResults_ScrapCosts | [@Company] | BlackBox | 0 | 1
Report | UspResultsRefresh_TableTimes | [@Exec] | BlackBox | 0 | 1
Report | UspResults_PurchaseOrderDetails | [@Company] | BlackBox | 0 | 1
Report | UspResults_PurchaseOrderChanges | [@Company] | BlackBox | 0 | 1
Report | UspResults_ArCustomers | [@Company] | BlackBox | 0 | 1
Report | UspResults_SalesOrders | [@Company] | BlackBox | 0 | 1
Report | UspResults_AccPayable_AgedInvoices | [@Company] | BlackBox | 0 | 1
Report | UspResults_UnpaidAssets | [@Company] | BlackBox | 0 | 1
Report | UspResults_GrnInvoiceDetails | [@Company] | BlackBox | 0 | 1
Report | UspResults_GenledgerJournalsGrouped | [@Company] | BlackBox | 0 | 1
Report | UspResults_UnpaidGRNAssets | [@Company], [@PeriodYYYYMM] | BlackBox | 0 | 1
Report | UspResults_StockMovements | [@Company] | BlackBox | 0 | 1
Report | UspResults_StockOutput | [@Company] | BlackBox | 0 | 1
Report | UspResults_Labour | [@Company] | BlackBox | 0 | 1
Report | UspResults_LabourGlCodes | [@Company] | BlackBox | 0 | 1
Report | UspResults_PurchaseOrdersOpen | [@Company] | BlackBox | 0 | 1
Report | UspResults_WipStockRequiredPerJob | [@Company], [@MasterJob] | BlackBox | 0 | 1
Report | UspResults_LotsProcessed | [@Company] | BlackBox | 0 | 1
Report | UspResults_ReservedLots | [@Company], [@Job], [@StockCode] | BlackBox | 0 | 1
Report | UspResults_PurchaseOrdersInvoices | [@Company] | BlackBox | 0 | 1
Report | UspResults_OutstandingPurchaseOrders | [@Company] | BlackBox | 0 | 1
Report | UspResults_GenMasterMapping | [@Company] | BlackBox | 0 | 1
Report | UspResults_LabourDetails | [@Company] | BlackBox | 0 | 1
Report | UspResults_ApSupplierNar | [@Company], [@Supplier] | BlackBox | 0 | 1
Report | UspResults_LotsRetesting | [@Company] | BlackBox | 0 | 1
Report | UspResults_JobHeader_AllJobs | [@Company], [@EndDateText], [@StartDateText] | BlackBox | 0 | 1
Report | UspResults_PurchaseOrders | [@Company] | BlackBox | 0 | 1
Report | UspResults_JobHeader | [@Company], [@Job] | BlackBox | 0 | 1
Report | UspResults_AmendmentJnl | [@Company] | BlackBox | 0 | 1
Report | UspResults_StockLevels | [@Company] | BlackBox | 0 | 1
Report | UspResults_AvailableLots | [@AmountRequired], [@Company], [@StockCode] | BlackBox | 0 | 1