## Project Status Dashboard
Qlik Sense |  |  | Project Status Dashboard
| Project Status |  | Completed |  | 5% |  | Outstanding Issues
| Ongoing Activities: 2 |  |  | Project Plan |  | Click on the gantt chart to see it in detail
| Activity | % done
| Finalise Quotes | 80%
| Recreate dashboards in Sense | 75%
| Create Project Plan | 90%
| Infrastructure Review | 10%
| Define Users | 5%
Top 5 Issues
Sign off on costs
Agree deployment structure
Training in Canada
Dashboard delivery plans
Business Testers
| Burndown Chart |  |  |  |  | Project Timeline

## Gantt Chart Template
Project Plan - Gantt Chart Template
|  | Planned |  | Actual |  | % | Show Gantt for | [5 empty] | Planned | [5 empty] | Show Status? |  |  |  |  | █ |  |  |  | What is current week? | [8 empty] | 1
# | List of Activities | Start | Dur | Start | Dur | Done | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
1 | Produce Quotes | 1 | 1 | 1 | 1 | 0%
2 | Sign off Quotes | 2 | 2 | 0 | 0 | 0%
3 | Transfer Syspro to FTP | 1 | 3 | 0 | 0 | 0%
4 | Transfer Syspro to Azure | 3 | 2 | 0 | 0 | 0%
5 | Deploy Reporting DB to Azure | 4 | 1 | 0 | 0 | 0%
6 | Define user groups | 3 | 1 | 0 | 0 | 0%
7 | Get Training Costs | 1 | 3 | 0 | 0 | 0%
8 | Define network security | 2 | 3 | 0 | 0 | 0%
9 | Define publication route | 3 | 1 | 0 | 0 | 0%
10 | Agree division of labour | 4 | 1 | 0 | 0 | 0%
11 | Set up of users and user groups | 4 | 1 | 0 | 0 | 0%
12 | Provision of application servers | 5 | 2 | 0 | 0 | 0%
13 | Provision of firewall | 5 | 2 | 0 | 0 | 0%
14 | provision of external proxy server | 5 | 2 | 0 | 0 | 0%
15 | Set up of application server | 7 | 1 | 0 | 0 | 0%
16 | set up of Qlik on proxy | 7 | 1 | 0 | 0 | 0%
17 | Deploy first report to test | 7 | 1 | 0 | 0 | 0%
18 | User Training | 8 | 1 | 0 | 0 | 0%
19 | testing by users | 8 | 3 | 0 | 0 | 0%
20 | deployment to live | 10 | 1 | 0 | 0 | 0%
21 | Activity | 0 | 0 | 0 | 0 | 0%
22 | Activity | 0 | 0 | 0 | 0 | 0%
23 | Activity | 0 | 0 | 0 | 0 | 0%
24 | Activity | 0 | 0 | 0 | 0 | 0%
25 | Activity 25 | 0 | 0 | 0 | 0 | 0%
26 | Activity 26 | 0 | 0 | 0 | 0 | 0%
27 | Activity 27 | 0 | 0 | 0 | 0 | 0%
28 | Activity 28 | 0 | 0 | 0 | 0 | 0%
29 | Activity 29 | 0 | 0 | 0 | 0 | 0%
30 | Activity 30 | 0 | 0 | 0 | 0 | 0%
31 | Activity 31 | 0 | 0 | 0 | 0 | 0%
32 | Activity 32 | 0 | 0 | 0 | 0 | 0%
33 | Activity 33 | 0 | 0 | 0 | 0 | 0%
34 | Activity 34 | 0 | 0 | 0 | 0 | 0%
35 | Activity 35 | 0 | 0 | 0 | 0 | 0%
36 | Activity 36 | 0 | 0 | 0 | 0 | 0%
37 | Activity 37 | 0 | 0 | 0 | 0 | 0%
38 | Activity 38 | 0 | 0 | 0 | 0 | 0%
39 | Activity 39 | 0 | 0 | 0 | 0 | 0%
40 | Activity 40 | 0 | 0 | 0 | 0 | 0%

## Backlog
Project Plan - Backlog
# | Activity | Task # | Task | Assigned To | Due Date | Count | Status | Details
1 | Produce Quotes | 1 | Define number of users | CJ/HM | 2016-02-25 | 1 | Complete | 5 users + 50 hours of access per month
1 | Produce Quotes | 2 | Agree level of support | CJ/HM | 2016-02-25 | 1 | Complete | daily checks and support
1 | Produce Quotes | 3 | Agree infrastructure location | CJ/HM | 2016-02-25 | 1 | Complete | Prometic's Azure platform
1 | Produce Quotes | 4 | Provide sliding scale of server requirements | Differentia | 2016-02-26 | 1 | Outstanding
1 | Produce Quotes | 5 | Provide Quote for Qlik licenses and setup | Differentia | 2016-02-26 | 1 | Outstanding
1 | Produce Quotes | 6 | Provide Quote for Azure infrastructure | HM | 2016-02-29 | 1 | Outstanding | Awaiting Task 4
2 | Sign off Quotes | 7 | Present Quotes to BP/GW/DF | CJ/HM | 2016-02-29 | 1 | Outstanding | Awaiting Task 6
2 | Sign off Quotes | 8 | Sign off Quotes | BP | 2016-03-11 | 1 | Outstanding | Awaiting Task 7
3 | Transfer Syspro to FTP | 9 | Request backup and transfer | HM | 2016-02-26 | 1 | Complete | Request sent 26/02
3 | Transfer Syspro to FTP | 10 | Action and automate transfer | K3 | 2016-03-11 | 1 | Outstanding
4 | Transfer Syspro to Azure | 11 | Grant CJ access to Azure | IT | 2016-03-01 | 1 | Outstanding
4 | Transfer Syspro to Azure | 12 | Write job to import files | CJ | 2016-03-04 | 1 | Outstanding | Awaiting Task 11
4 | Transfer Syspro to Azure | 13 | define and build error reports | CJ | 2016-03-10 | 1 | Outstanding | Awaiting Task 12
5 | Deploy Reporting DB to Azure | 14 | Deploy Reporting DB to Azure | CJ | 2016-03-11 | 1 | Outstanding | Awaiting Task 13
6 | Define user groups | 15 | Define different types of reports | CJ | 2016-03-18 | 1 | Outstanding
6 | Define user groups | 16 | Define different levels of data | CJ | 2016-03-18 | 1 | Outstanding
6 | Define user groups | 17 | Choose first deployment users | ? | 2016-03-25 | 1 | Outstanding
6 | Define user groups | 18 | Choose Super Users | ? | 2016-03-25 | 1 | Outstanding
6 | Define user groups | 19 | Assign users to groups | ? | 2016-03-25 | 1 | Outstanding
7 | Get Training Costs | 20 | Get Training Costs | CJ | 2016-03-18 | 1 | Outstanding
8 | Define network security | 21 | Review of network diagram by IT & Differentia | IT | 2016-03-04 | 1 | Outstanding
9 | Define publication route | 22 | Agree change control form | CJ/HM | 2016-04-01 | 1 | Outstanding
9 | Define publication route | 23 | Agree access to test server | CJ/HM | 2016-04-01 | 1 | Outstanding
9 | Define publication route | 24 | Agree sign off and go live process | CJ/HM | 2016-04-01 | 1 | Outstanding
10 | Agree division of labour | 25 | Define what infrastructure exists and what needs to be setup | IT | 2016-03-25 | 1 | Outstanding
10 | Agree division of labour | 26 | define at what point Differentia take over configuration | IT | 2016-03-25 | 1 | Outstanding
10 | Agree division of labour | 27 | Define internal issues vs those to be raised to Differentia | IT/CJ | 2016-03-25 | 1 | Outstanding
11 | Set up of users and user groups | 28 | Create users and groups in Azure AD | IT | 2016-04-01 | 1 | Outstanding | Awaiting Task 19
12 | Provision of application servers | 29 | Provision of live server | IT | 2016-04-01 | 1 | Outstanding | Awaiting Task 8
12 | Provision of application servers | 30 | Provision of test server | IT | 2016-04-01 | 1 | Outstanding | Awaiting Task 8
13 | Provision of firewall | 31 | Provision of firewall | IT | 2016-04-01 | 1 | Outstanding | Awaiting Task 8
14 | provision of external proxy server | 32 | provision of external proxy server | IT | 2016-04-01 | 1 | Outstanding | Awaiting Task 8
15 | Set up of application server | 33 | Set up of live server | Differentia | 2016-04-08 | 1 | Outstanding | Awaiting Task 29
15 | Set up of application server | 34 | Set up of test server | Differentia | 2016-04-08 | 1 | Outstanding | Awaiting Task 30
16 | set up of Qlik on proxy | 35 | set up of Qlik on proxy | Differentia | 2016-04-08 | 1 | Outstanding | Awaiting Task 32
17 | Deploy first report to test | 36 | Deploy first report to test | CJ | 2016-04-08 | 1 | Outstanding | Awaiting Task 35
18 | User Training | 37 | Agree approach internal vs external | ? | 2016-03-01 | 1 | Outstanding | Awaiting Task 36
19 | testing by users | 38 | Internal testing - access to system | CJ/HM | 2016-04-08 | 1 | Outstanding | Awaiting Task 37
19 | testing by users | 39 | define users to conduct testing | CJ/HM | 2016-03-25 | 1 | Outstanding | Awaiting Task 38
19 | testing by users | 40 | User testing - report data and functionality | ? | 2016-04-15 | 1 | Outstanding | Awaiting Task 39
20 | deployment to live | 41 | following sign off, move report to live server | Differentia | 2016-04-15 | 1 | Outstanding | Awaiting Task 40

## Issue Tracker
Issue Tracker Template
Date
# | Issue | Priority | Open | Close | Comments
1 | Training in Canada | High | 2016-02-26 |  | How to deliver user training in Canada
2 | Dashboard delivery plans | Low
3 | Business Testers | Medium | 2016-02-26 |  | Which users will be involved in testing - that have time to test?
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60

## Burndown Chart
Burn down chart
Deliverable Burn Down
| Burned down |  | Balance |  | Daily Completed
Day | Planned | Actual | Planned | Actual
0 |  |  | 61 | 61 | #N/A
1 | 6 | 4 | 55 | 57 | 4
2 | 6 |  | 49 | #N/A | #N/A
3 | 4 |  | 45 | #N/A | #N/A
4 | 3 |  | 42 | #N/A | #N/A
5 | 7 |  | 35 | #N/A | #N/A
6 | 8 |  | 27 | #N/A | #N/A
7 | 5 |  | 22 | #N/A | #N/A
8 | 20 |  | 2 | #N/A | #N/A
9 | 2 |  | 0 | #N/A | #N/A
10 |  |  | 0 | #N/A | #N/A
11 |  |  | 0 | #N/A | #N/A
12 |  |  | 0 | #N/A | #N/A
13 |  |  | 0 | #N/A | #N/A
14 |  |  | 0 | #N/A | #N/A
15 |  |  | 0 | #N/A | #N/A
16 |  |  | 0 | #N/A | #N/A
17 |  |  | 0 | #N/A | #N/A
18 |  |  | 0 | #N/A | #N/A
19 |  |  | 0 | #N/A | #N/A
20 |  |  | 0 | #N/A | #N/A

## Data
Enter Project Status |  | Enter the Project Milestone Data Here |  |  | Top 5 Issues
Overall Project Status | Green | Date | Milestone if any | Height | Issue | Dummy
Overall Project Progress | 5% | 2015-11-01 |  |  | Sign off on costs | 0
|  | 2016-01-01 | Indepth review of Qlik Sense | 1 | Agree deployment structure | 0
Enter Activity Details |  | 2016-02-01 |  |  | Training in Canada | 0
|  | 2016-03-01 | Quotes & Sign Off | 2 | Dashboard delivery plans | 0
|  | 2016-04-01 | Set up of servers & rollout of reports | 3 | Business Testers | 0
Ongoing Activities | 2 | 2016-05-01 |  |  |  | 0
|  | 2016-06-01 | Review of usage and dashboards | 1 |  | 0
List of Activities |  | 2016-07-01 |  |  |  | 0
|  | 2016-08-01 |  |  |  | 0
Activity | Completion | 2016-09-01 |  |  |  | 0
Finalise Quotes | 80% | 2016-10-01 |  |  |  | 0
Recreate dashboards in Sense | 75% | 2016-10-01 |  |  |  | 0
Create Project Plan | 90%
Infrastructure Review | 10%
Define Users | 5%
Note on K3: Donot edit this

## Calculations (hidden)
Open Issue Summary
High | 1
Medium | 1
Low | 1

## Legend (hidden)
Types of Gantt | Gantt Chart Symbols
Planned | █
Actual | ○
↓